## Framework
CILT International | [6 empty] | Control version 7 Released 11 11 16
Education Strategy Framework | [6 empty] | Red font - changes from last version
|  | Status/ On Track | Ref No | Objective | How | Who | When | Investment Requirement | Priority
| Process |  | 1.1 | For all accredited and prospective training and education providers to be following the approved accreditation and registration process to time and budget | Reinforce the new formal accreditation and registration processes and the fee rules associated with them. Regularly monitor progress through a monthly dashboard process. Remove accreditation and trading agreements/rights where process is not followed. Keep MOU under constant review Train the Trainer online package developed to ensure consistency in CILT training delivery | CILT International via the IPDC and CILT Ireland. Territories and Branches will reinforce the system. | Process reinforced in Q3/Q4 with stricter enforcement now in place. No certification issued without payment and registrations must follow the process in the guidelines | Covered by 2014 expenditure on new database system and associated process improvements. Due to specific country needs some additional spend will be needed in FY2016 and has been identified within the budget | 1
|  |  | 1.2 | For all accredited education providers to be able access materials, resources and guidance online | Via the new CILT International website and cloud store Set up a voluntary licence arrangement to allow downloads within FY16 and then incorporate into the automatic accreditation process. | CILT International via CW/KN/JH input | Jun 15 for basic downloads (phase 1 website) 2016 gradual implementation then moving to full functionality in 2017 | Software investment as part of CILT International website and cloud specification. | 3
|  |  | 1.3 | To develop and deliver an effective dashboard with all essential KPIs, measuring both operational performance and strategy delivery | Agree KPIs, method of measurement and publish results on a regular basis | CILT International | April 15 for the system and first full dashboard in Dec 15 Quarterly dshboard reporting to IMC | Covered by investment in the new database system and IPDC/Education Administrator/ CILT Ireland time | 1
|  |  | 1.4 | For all Territories and Branches to have Education Committees capable of supporting product development, accreditation and CPD processes | Appoint Education Champions and Chairs within each Branch and Territory responsible for delivering the Education Strategy | IPDC, Chairs of IESC/IMC, Branch and Territory Presidents | Dec 15 for Champions 85% coverage post Convention Changes in Branch contacts to be promptly communicated Now 95% coverage | Time investment as part of overseas visits carried out by PB/JS/KN/JH and senior CILT team | 2
|  |  | 1.5 | To increase the number of active training providers in each country | Through strategic partners, country-based training providers, referrals and direct applicants | IPDC, Education Champions | Intensification of activity based on priority income streams | IPDC and local investment | 1
| Profile |  | 2.1 | For all of our Territories to have CILT qualifications formally recognised by Government and for 50% of Branches to have also achieved this threshold | Assessment of recognition of CILT qualifications across all Branches and Territories CILT International commits to support local campaigns to become recognised by qualifications authorities and Govt Ministries To achieve formal regulated status for CILT International syllabus to complement CILT UK | IPDC, Education Champion and Chairs, Presidents | Jun 15 (assessment completed) June 2017 (all Territories)* Revised timeline to take account of India, Nigeria etc. Dec 17 (50% of all Branches) | Time investment as part of overseas visits carried out by PB/JS/KN/JH and senior CILT team plus IPDC time | 3
|  |  | 2.2 | For all Territories and Branches to have in place an active Education Champion | IPDC to communicate requirements to Branches and Territories with role specification | IPDC/Presidents | Jun 15- 80% achieved Jun 16 - 100% (post convention) - now achieved for all established country organisations | Time investment from Branches and Territories , IPDC time | 1
|  |  | 2.3 | For CILT to be recognized as the key ‘go to’ provider in the market for the development of bespoke training, education and apprenticeship programmes within the transport and logistics sector across at least 50% of all countries (Potentially a shared vision across the wider portfolio - requiring IMC support and strategic assistance) | Use of 3 routeways to achieving the objective: Via the Global Training Directory Via Branch in a Box tools Via local Branch and Territory activities | IPDC/KN/CW IPDC/KN/CW Local education reps | Sept 15 Dec 15 Ongoing | IPDC and Secretariat time Support from Branches and Territories IMC corporate suport needed | 3
|  |  | 2.4 | For CILT branded qualifications and courses to be recognised as the first choice option for high quality transport and logistics training | Marketing and promotion of CILT professional development offerings to maximise uptake and sales through Government recognition and accreditation Global Training Directory Local marketing, conference and trade events (at least 2 significant events a year) Focused drive on India, Oman/GCC during Q1/Q2 | IPDC/KN/CW Local Branch officers External partners | May 2016 (Marketing plan) - deadline to be reset Dec 16 for event programme to be fully in place | Global Training Directory will require resource time from IPDC and £5k development budget Local marketing opportunities will rely on Branch and Territory budgets | 3
| Product |  | 3.1 | For all levels of CILT qualifications to be up-to-date and offered through high-quality, capable approved training providers across the CILT family | Refresh and rewrite our core education courses (Levels 1-6) ensuring none are older than 3 years Achieve agreement with the UK on timings Meet market demand by jointly produced modules which will allow more flexibility | IPDC/CILT UK | Entry Award - Mar 15: Refresh 2018 Diploma - Mar 15: Refresh 2018 Advanced Diploma - Sept 15 launched Refresh 2018 Intro Cert - Refresh 2017 Cert - Refresh 2017 | IPDC time, CILT UK Awarding Organisation resources, development budget covered through CILT International licence fees to CILT UK Assessment needed on which products/modules are most popular for international markets is critical | 2
|  |  | 3.2 | For a global online training directory to cross-broker CILT accredited, endorsed & partnered products, including conference and short course promotion | Creation of a one stop shop portal for CILT approved training and development opportunities between Branches and Territories Facilitation and capacity building service at this stage | IPDC/KN/CW | Sept 15 - GTD framework completed ready for B2B knowledge sharing and B2C basic search facility for employers/ students etc Dec 15 onwards - population with all country information Go live - May 2016 Ongoing updating throughout 2016/17 | Resource time from IPDC to lead project and £5k development budget (software). Time for collating info from Branches/Territories Training Providers | 1
|  |  | 3.3 | For a portfolio of unit modules, endorsed CPD and short course offerings to be provided on a global basis | Assessment of quick win existing opportunities through a trawl of all current Territory and Branch offerings Dynamic review and maintenance of opportunities and quality assurance support Develop new CPD/short course products for international markets (niche topic areas, coaching and leadership development) | IPDC IPDC/CILT UK IPDC/CILT Ireland and other key territories/branches | End Q2 2016 Ongoing via IPDC | IPDC and Education Champion time IPDC time so set up monitoring system and Education Champions to complete | 3
|  |  | 3.4 | For selected qualifications to be delivered on an e-learning basis with options for exam-based/controlled assessment or on-line testing | Conversion of our existing CILT International core qualifications to an appropriate e-learning platform For at least 50% of the product turnover to be covered through on-line and e-enabled services To explore the model for delivery including strategic partners/UK input | IPDC/CILT UK | Original targets Dec 16 (wave 1) and Dec 17 (wave 2) Blernded learning options being developed in Oman, South Africa and South India to allow remote access learning/webinars etc alongside taught programmes/exams Full E learning conversion not recommended / feasible at present | IPDC, CILT UK, CILT Ireland , South India project, South Africa Technology platform would require budget/partner to be sourced | 2
| Professionalism |  | 4.1 | For all CILT countries to have completed a local Education Delivery Plan | Education Champions to lead the Delivery Plan on A Page process using the model provided Mandate the Plan on a Page approach via IMC | IPDCC/Education Champions/Chairs Chairs IESC/IMC | April 2016 inc review of Annual Report (to feed in Convention) Reinforce Convention 2016 - New/ Refreshed Branches are achieving. Will require refresh at Convention 2017 | Education Champions and Education Committees plus IPDC quality assurance time | 1
|  |  | 4.2 | For a CPD toolbox and baseline international CPD system to be made available across the CILT family | Integrate CPD toolbox into Branch in A Box International CPD scheme and points system (UK/Australia) For all CILT countries to have in place a quality approved mentoring scheme | IPDC/KN IPDC/SW/DdeC/KH IPDC/Education Champions/Chairs | Dec 15 May 16 - CPD toolkit launch CILT UK adopted and have gone liver Oct 2016 Key article in CILT UK Focus journal | IPDC resource time and allow for on line production costs IPDC to develop template and Education Champions/Chairs to develop and promote locally | 1
|  |  | 4.3 | For all CILT countries and regional groupings to thought partner with government departments to address national challenges and shape education policy | Participate in national level transport and logistics Committee and decision-making boards Make evidence recommendations about specific skills gaps in industry | Education Champions/Chairs Education Champions/Chairs | Dec 15 - 50% to participate - review success rate through Annual Reports Dec 17 - all Branches and Territories to be contributing | IPDC to provide support tools as part of the Branch in A Box project Education Champions/Chairs to work actively with CILT Policy Committee Chairs - time resource | 2
|  |  | 4.4 | For all countries to be running at least 2 strategic national CILT professional conference and events per year, endorsed by government and industry | Organise 'open' industry events focused on country specific issues and themes. | Branch or Territory Events/Education Committees | Dec 16 for all operational countries - Territories achieving target in general with some significantly exceeeding. 30% of mature Branches achieving | Branch and Territory time and funding - with intention to make cost neutral through partnering/contra deals | 2
| Pricing |  | 5.1 | For CILT qualifications to be offered based on their true market value to each economy, whist ensuring they are affordable to the end customer. | Complete competitor and market benchmarking process to inform future pricing Critical activity to inform FY2017 projections and pricing Implement value pricing for all CILT International accreditations and qualifications including quality value | IPDC /Education Champions IESC/IMC | Competitor analysis delveoped on ad hoc baasis where support given by Branches and Teirritoies. Comprehensive pricing/costs review and business model options to be reported end Q1 2017 as value pricing model not being adopted | IPDC to assess pricing system and make recommendations - time resources | 1
|  |  | 5.2 | For CILT International income streams to be diversified so as not to rely on qualification income alone, but through corporate training, short/modular courses and brokerage services | Work with Education Champions and providers to establish needs and priorities Identify 'Top 50' global organisations that would use CILT International products Brokerage services to be established as part of the Global Training Directory offering | IPDC/Education Champions JS/PB IPDC/JS/KN | Survey April 2016 and feed into FY16 activity and Convention Feed into corporate membership strategy Jan 2016 onwards (CILT Ireland pilot) Jan 2017 next wave of GTD materials added to dataset | IPDC and Education Administrator time allocation JS/PB time allocation IPDC/KN/JH and software support (included above) | 2
|  |  | 5.3 | For CILT International, as a business unit, to have achieved a 20%+ annual uplift in turnover in order to generate enough margin to invest in product development | Achieve 20% uplift in full price paying students each year (1950 students for 2015) Uplift in the number of active accredited providers by at least 10 per year (minimum of 50 students each) Monitoring of student bookings/registrations and cashflow throughout yearly cycle to manage financial profile | IPDC/training providers IPDC/KN/training providers | Dec 15 - turnover of 2050 students based on t/o of £280,000 and average fee of £130 per student - achieved Dec 15 - 20+ new/accredited providers in 2015 Dec 16 - £330,000 turnover and >2500 students based on £130 per student Dec 17 - £350,000 turnovewr based on new providets and increase in fees | IPDC time with training provider time IPDC and accreditation consultant pool - relies on up front fee income to make accreditation process cost neutral | 1

## Roadmap
CILT International | [20 empty] | Control version 8 - 23/1/17
Education Strategy Roadmap - Review Date - 7/4/17 | [7 empty] | * | = Completed |  |  | Red font - changes from last version
| Strategy | Strategy | Headline Objective | Overall | 2015 |  |  |  | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019
| Pillar | Action |  | Status | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Process | 1.1 | Providers following process
|  | 1.2 | Access to resources |  |  |  | *website | CRM
|  | 1.3 | Dashboard
|  | 1.4 | Education Committees
| Profile | 2.1 | Government recognition
|  | 2.2 | Education Champions
|  | 2.3 | Go to' thought partner
|  | 2.4 | First choice option
| Product | 3.1 | CILT qualifications / KKA |  |  |  | Adv Dip | [5 empty] | UK Review | KKA Int Conv | IESC June
|  | 3.2 | Online training directory |  |  |  |  | website * |  |  |  |  | Refresh
|  | 3.3 | CPD and short courses
|  | 3.4 | E learning
| Professionalism | 4.1 | Local Education Plan | [9 empty] | ongoing mentoring required
|  | 4.2 | CPD Toolbox |  |  |  | framework* | [6 empty] | *update
|  | 4.3 | Government collaboration
|  | 4.4 | National conferences
| Pricing | 5.1 | Market value/competitor analysis | [11 empty] | *update
|  | 5.2 | Income diversification
|  | 5.3 | 20% uplift in turnover annually | [8 empty] | review
| Strategy Refresh | S1 | Initial review of monitor/strategy | [8 empty] | JH/JS | JH/JS
|  | S2 | Review Reporting on 3 yr Ed Strat | [10 empty] | Int Conv | IESC June
|  | S2 | Revised Education Strategy | [10 empty] | Int Conv | IESC June
|  | S3 | Revised Monitor regime | [11 empty] | IESC June