## Project Plan and Gantt Chart
CILT Project Gantt Chart |  |  |  | A Visual timeline to see details about each CILT Ph task as well as project dependencies. | [13 empty] | A Visual timeline to see details about each CILT Ph task as well as project dependencies. | [13 empty] | A Visual timeline to see details about each CILT Ph task as well as project dependencies. | [13 empty] | A Visual timeline to see details about each CILT Ph task as well as project dependencies.
| TASK TITLE | Task Lead/Owner | Target Date | PCT OF TASK COMPLETE | CILTPh Approval and Go-Signal | [11 empty] | CILT Ph Implementation (PHASE ONE - 2020) | [13 empty] | CILT Ph Promotion and Execution (PHASE TWO - 2020) | [12 empty] | CILT Ph Events and Establishments | [5 empty] | CILT Ph Membership Drive
[5 empty] | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | Q3 2020 |  |  | Q4 2020 |  |  | Q1 2021 |  |  | Q2 2021 |  |  | Q3 2021 |  |  | Q4 2021
[5 empty] | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
1 | CILT Ph Conception and Initiation
1.1 | Business Plan Creation and Finalization
1.1.1 | Business Plan Creation | Karyn Welsh and CILT Ph | - | 100%
1.1.2 | Business Plan Review and Approval | CILT Int'l and Keith Newton | 2019-10-08 | 100% | Decision from CILT Int'l
1.1.3 | Roll-out Plan Signoff | CILT Ph Karyn Welsh and CILT Int'l | 2020-01-24 | 100%
1.2 | Organization and Partnership
1.2.1 | CILT Australia and CILT Ph National Council Engagement and Concurrence Meeting | Karyn Welsh and CILT Ph National Council | Monthly | Work in Progress |  |  |  | 10/23/2019 - Project Plan Meeting | 11/11/2019 - Project Plan Meeting
1.2.2 | CILT Philippines National Council (Internal Processes for meetings, minutes and updates) | CILT Ph National Council | Monthly | Work in Progress
1.2.3 | CILT International Invited to Update Meetings | Karyn Welsh and CILT Intl | Quarterly | Work in Progress
2 | CILT Ph Membership
2.1 | CILT Ph Engagement and Concurrence Meeting
2.1.4 | CILT Ph Bank Account |  |  | 100%
2.1.5 | Operational Budget FY 2021 | Karyn Welsh and CILT Intl | 2020-12-30
2.2 | CILT Ph Website Design and Development |  | 2020-12-30
2.2.1 | Gathering Information Planning: Sitemap and Wireframe Creation Design: Page Layouts, Review, and Approval Cycle Coding | CILT Ph and Karyn Welsh |  | Work in Progress
2.2.2 | Funding and reimbursement approval process (Established) | CILT Ph and Karyn Welsh |  | 100%
2.3 | Membership Drives | CILT Ph | 2020-07-01 | Work in Progress
2.3.2 | Advertising and Promotion |  |  | Work in Progress
2.3.3 | Membership Roundtable and Events (Quarterly) |  |  | Work in Progress
2.4 | Establish Event Program |  |  | Work in Progress
2.4.1 | The Critical Role of Supply Chain Management During Pandemic |  |  | 100%
2.4.2 | Challenges of Supply Chain Intermodal Logistics in times of Pandemic |  |  | 100%
2.4.3 | COVID 19 in the Context of Transport and Logistics (Vice President Philippines) |  | Dec/Jan | TBC
2.5 | Sponsorship (Corporate Membership)
2.5.1 | Sponsorship Pack Development with CILT Australia |  | Q2 2021 | 0%
2.5.2 | Promotion for sponsorship |  | Q2 2021 | 0%
2.5.3 | Advertising Sponsors |  | Q2 2021 | 0%
2.5.4 | Engaging in joint activities with Sponsors |  | Q2 2021 | 0%
2.6 | Education committee | Karyn Welsh and Marjorie Rola |  | Work in Progress
2.6.1 | Training from Australia on CPD |  |  | 0%
2.6.2 | CPD assessment training for members |  |  | 0%
2.6.3 | Recognised and Certified Courses |  |  | 0%
2.6.4 | Advertisement of the courses |  |  | 0%
3 | CILT Ph Quick wins
3.1 | Community Awareness and Participation Plan Focuses on Metro Manila |  | July 2020 - Q4 2021 | 0%
3.1.1 | Roundtable meeting with C-Levels Executives from Logistics and Transport field |  | Q2 2021 - Q4 2021 | 0%
3.1.2 | Collaboration/Tie up seminars |  | Q3 2021 - Q4 2021 | 0%
3.1.3 | Conduct 3 webinars under 2020 |  | Q3 2020 - Q4 2020 | 70%

## Philippine Holiday
The regular holidays are:
January 1, 2021, Friday - New Year's Day
April 1, 2021, Maundy Thursday
April 2, 2021, Good Friday
April 9, 2021, Friday - Araw ng Kagitingan
May 1, 2021, Saturday - Labor Day
June 12, 2021, Saturday - Independence Day
August 30, 2021, last Monday of August - National Heroes' Day
November 30, 2021, Tuesday - Bonifacio Day
December 25, 2021, Saturday - Christmas Day
December 30, 2021, Thursday - Rizal Day
Special non-working days:
February 12, 2021, Friday - Chinese New Year
February 25, 2021, Thursday - EDSA People Power Revolution Anniversary
April 3, 2021 - Black Saturday
August 21, 2021, Saturday - Ninoy Aquino Day
November 1, 2021, Monday - All Saints' Day
December 8, 2021, Wednesday - Feast of the Immaculate Conception of Mary
December 31, 2021, Friday - last day of the year
Additional special non-working holidays:
November 2, 2021, Tuesday - All Souls' Day
December 24, 2021, Friday - Christmas Eve