## Project Account
$1 = 450 kzt - February - May $1 = 415 kzt - June - July $1 = 420 kzt - August $1 = 430 kzt - Sept - Oct
CILT Kazakhstan |  |  |  |  | 2021 |  |  |  | 2021 |  |  |  | 2021 |  |  |  | 2021
Project (USAID) account (with online delivery) |  | Jan | Feb | March | April | May | June | July | August | September | October | November | December | Show a predicted model for Sept- March inclusive * |  | January 2021 |  | Мay 2021
- | Opening balance at with CILT Kaz at 1/9/20 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | TOTAL | Notes
DAI Payments when it received in bank |  | 17386.7 | 17600 | 11520.15 | 20320 |  | 19800 |  |  | 8800 |  |  |  | 95426.85
USL Project Income |  |  |  | 2000 | [9 empty] | 2000
Leftover from 2020 Opening balance |  | 1523.15 | [11 empty] | 1523.15
0
Revenue from Phase 2 activities Corporate Membership and BSP revenue |  |  | 2630 | 3244 | 2895 | 2895 | 2895 | 2895 | [5 empty] | 17454 | Minimun of 25 Corporate members under CTJ Project
Costs and expenses
Workstream 1
Develop trainer pool | [13 empty] | 0
Develop road map | [13 empty] | 0
Translation of new materials |  |  |  | 2510 | -1020 |  | -510 | [6 empty] | 980 | Modules translated: M1-L2, M1-L3, M2-L3, DIP05, DIP10, DIP 13 Planning to translate 5 more modules
Adaptation of the translated materials | [5 empty] | -945 |  | -326 | [5 empty] | -1271 | This includes adaptation of Phase 1 and 2 materials
Academic trainer supporting activities in organizing CILT courses | [13 empty] | 0
Marketing campaign, promotion programme & marketing materials (banners, brochures and etc.), including purchasing an equipment (printer, papers and etc.) |  | -288 | -288 | -288 | -288 |  |  |  |  | -288 | -288 | -288 | -288 | -2304
Website and Marketing tool on CILT Kaz website development and website support service |  |  |  | -244 | -244 | -244 | -244 | -244 | [5 empty] | -1220
Networking events (master classes, seminars, round tables and etc) |  | -344 | -344 | -688 | -688 | -344 |  |  |  | -688 | -688 | -688 | -688 | -5160 | Key savings here
Workstream 2 | [14 empty] | Key savings put in this stream
Implementation of CILT Membership full services (career support services, legal support services) |  |  | -512 |  | -512 |  | -512 |  | -512 |  | -512 | 0 | -512 | -3072
Implement CILT Int standards and accreditation | [13 empty] | 0
CILT brand recognition strategy and model development / Marketing activities including Translation of marketing materials |  | -385 |  | -756 |  | -756 |  | -756 |  | -756 |  | -756 |  | -4165 | This includes promoting Instagram, Facebook, YouTube accounts using third-party services, sponsoring activities, translation of brand videos and materials, developing content by third-party providers and etc. On average $750 a month
Develop formal partnerships with institutions | [13 empty] | 0
Establishment of Central Asian Hub | [13 empty] | 0
WiLAT activities (total budget $13200) |  | -284 | -3465 | -2566 | -1344 | -640 | -640 | -640 | -640 | -640 | -640 | -640 | -640 | -12779
Next Generation (total budget $5000) |  |  | -2000 | -800 | -450 | -450 | -450 | -450 | -400 |  |  |  |  | -5000
CILT Int Webinars- Translation, Dubbing | [13 empty] | 0
CILT Kaz Webinars - Organization expenses | [13 empty] | 0
CILT Newsletters - Bulletins and Local Newsletters | [13 empty] | 0
Workstream 3
Build an "off the shelf" consultancy model for BSP's to use | [13 empty] | 0
Train BSPs in consultancy model and best practice | [13 empty] | 0
Develop roadmap with BSP's and build support mechanism | [13 empty] | 0
Financial support for organisations - Payment to advisors for consultations services |  | 0 | -789 | -973.2 | -868.5 | -868.5 | -868.5 | -868.5 | [5 empty] | -5236.2
BSP Marketing including Translation of materials | [13 empty] | 0
General Expenses
Almaty office rent | Open since Sept 2019 | -609 | -609 | -800 | -800 | -800 | -800 | -800 | -800 | -800 |  |  |  | -6818
Astana office rent |  |  |  | -600 | -600 | -600 | -600 | -600 | -600 | -600 |  |  |  | -4200
Travel and expenses |  | -708 | -407 | -921 | -921 | -921 | -407 | 0 | 0 | -921 | -921 | -921 | -921 | -7969
Infrastructure for carrying out training, coffee break | [13 empty] | 0
Subscriptions - (Zoom, website hosting, Cloud, YouTube marketing, LinkedIn) |  | -105 | -105 | -105 | -105 | -105 | -105 | -105 | -105 | -105 | -105 | -105 | -105 | -1260
CILT Kazakhstan Project Management, tax included | Taxes included: At the expense of employer: Social security - 2.7% Liabilty Medical Insurance -2% Social tax - 6% At the expense of employee: Individual Income Tax - 9% Liability Pension - 10% Medical insurance - 2%
Aibek Kurmanov |  | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -12600
Erbol Muhaev |  | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -1050 | -12600
Arai Maratkyzy |  | -653 | -653 | -653 | -653 | -653 | -653 | -653 | -653 | -653 | -653 | -653 | -653 | -7836
Part-time employees and Buffer funds for salary coverage (safety funds) |  | -247 | -247 | -247 | -247 | -247 | -247 | -247 | -247 | -247 | -247 | -247 | -247 | -2964
CILT International contributions (20% tax included) | [13 empty] | 0
Total |  | 13186.85 | 8711 | 7532.95 | 12374.5 | -6778.5 | 14558.5 | -4894.5 | -6057 | 1002 | -6154 | -6398 | -6154 | 20929.8
Cashflow |  |  | 21897.85 | 29430.8 | 41805.3 | 35026.8 | 49585.3 | 44690.8 | 38633.8 | 39635.8 | 33481.8 | 27083.8 | 20929.8
Note on D5: Aibek: Phase 2 extension money will hit the account starting Feb

## StudentMember (BAU) Account
Forecasted Student Account plus Actuals for Membership | $1 = 420 kzt - 2021 | [9 empty] | NOTE CTJ PROJECT INCOME ENDS FROM DAI (USAID)
CILT Kazakhstan |  |  | 2021 |  |  |  | 2021 |  |  |  | 2021
Students account |  | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
| Opening balance | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | TOTAL | Notes
Revenue
Revenue from Level 5 Diploma Students (English and Russian Diploma) | 5451 | 1660 | 1166 | 3568 | 3568 | 3568 | 5478 | 5478 | 5478 | 5478 | 5478 | 5478 | 6204 | 58053
Corporate Membership and BSP Revenue |  | 2021 Oct: 1400; 2021 Nov: 1400; 2021 Dec: 700 | 3500 | 5 Corporate members
Membership for 2021 |  |  |  | 355 | 355 | 355 | 355 | 355 | 355 | 355 | 355 |  |  | 2840
Expenses
Corporate Membership and BSP Expenses |  | 2021 Oct: -420; 2021 Nov: -420; 2021 Dec: -210 | -1050
Student registration fee + 20% Tax |  | 2021 April: -3000; 2021 Oct: -3000 | -6000
Training room rent | [13 empty] | 0
Trainers salary (including Tax) |  | 2021 Feb: -1360; 2021 April: -2874; 2021 June: -2874; 2021 Aug: -2874; 2021 Oct: -4210; 2021 Dec: -4210 | -18402
Additional adaptation of training materials |  | 2021 Feb: -465; 2021 April: -465; 2021 June: -465 | -1395
Miscellaneous (marketing materials, printing, certficates, certificate frames, business lunches, business gifts, furniture, office renovation, travel) |  | Jan: -445; 2021 March: -445; 2021 May: -445; 2021 July: -445; 2021 Sept: -445; 2021 Nov: -445; 2021 Dec: -445 | -3115
Accounting services |  | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -1440
Bank fees (transaction fees - local and International) |  | -18 | -18 | -18 | -18 | -18 | -18 | -18 | -18 | -18 | -18 | -18 | -18 | -216
Staff salary - Izteleova Maral (Based on KPI for forming student groups) |  |  |  | -1430 | -1430 | -1430 | -1430 | -1430 | -1430 | -1430 | -1430 | -1430 | -1430 | -14300
Almaty office rent - under project cost to Sept 2021 |  | 2021 Oct: -800; 2021 Nov: -800; 2021 Dec: -800 | -2400
Astana office rent - under project cost to Sept 2021 |  | 2021 Oct: -600; 2021 Nov: -600; 2021 Dec: -600 | -1800
Taxes |  | 0 | 0 | 0 | -600 | 0 | 0 | 0 | 0 | 0 | -600 | 0 | 0 | -1200
Financial Audit for CILT international |  | 2021 Dec: -10000 | -10000
Total monthly costs and expenses | 5451 | 1077 | -797 | 1910 | -4584 | 1910 | 926 | 3820 | 1391 | 3820 | -3965 | 3045 | -10929 | 3075
Cashflow |  |  | 5731 | 7641 | 3057 | 4967 | 5893 | 9713 | 11104 | 14924 | 10959 | 14004 | 3075

## Project Account - 2020
$1 = 450 kzt - February - May $1 = 415 kzt - June - July $1 = 420 kzt - August $1 = 430 kzt - Sept - Dec $1 = 420 kzt Jan-Dec 2021
CILT Kazakhstan |  |  | 2020 | [12 empty] | 2021
Project account (with online delivery) |  | Jan-Feb costs prior to project starting | March | April | May | June | July | August | Sept | Oct | Nov | Dec |  |  | January 2021 |  | Мay 2021
- | Opening balance at with CILT Kaz at 1/9/20 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | TOTAL | Notes
|  | $ | $
DAI Payments - (Original Phase 2 funds are in Yellow) |  |  | 26520 | 17680 |  | 7170.69 | 27602.71 | 17386.7 | 8693.35 |  | 17386.7 |  | 122440.15
Money taken from second account- donated not loan |  | 4259 | [10 empty] | 4259
Leftover from Phase 1 after paying off to CILT Int In Dec 2019 - stays in this account |  | 1843 | [10 empty] | 1843
0
Revenue from Phase 2 activities | [12 empty] | 0
Costs and expenses
Workstream 1
Develop trainer pool |  |  | -7226 | [9 empty] | -7226
Develop road map |  |  | -3173 | [9 empty] | -3173
Translation of new materials |  |  |  | -5979 | [8 empty] | -5979
Adaptation of the translated materials |  |  | -1267 | -814 | -367 | -594 | -726 | -945 | -326 |  |  |  | -5039
Academic trainer supporting activities in organizing CILT courses |  | -127 | -167 | [9 empty] | -294
Marketing campaign, promotion programme & marketing materials (banners, brochures and etc.), including purchasing an equipment (printer, papers and etc.) |  | -416 | -244 | -462 |  |  |  | -182 | -126 | -288 |  |  | -1718
Website and Marketing tool on CILT Kaz website development and website support service |  |  |  | -854 |  |  |  | -506 | -2040 | -381 |  |  | -3781
Networking events (master classes, seminars, round tables and etc) |  | -260 | -87 | [8 empty] | -152 | -499 | Key savings here
0
0
0
0
0
Workstream 2 | [13 empty] | Key savings put in this stream
Implementation of CILT Membership full services (career support services, legal support services) |  |  | -136 | [9 empty] | -136
Implement CILT Int standards and accreditation | [12 empty] | 0
CILT brand recognition strategy and model development / Marketing activities including Translation of marketing materials |  |  |  |  | -381 | -866 | -812 | -634 | -537 | -589 | -385 |  | -4204
Develop formal partnerships with institutions | [12 empty] | 0
Establishment of Central Asian Hub | [12 empty] | 0
WiLAT activities | [9 empty] | -421 |  |  | -421
Next Generation | [12 empty] | 0
CILT Int Webinars- Translation, Dubbing |  |  |  | -956 | -2351 | -3153 | -2022 | -728 | -1100 | 0 |  |  | -10310
CILT Kaz Webinars - Organization expenses |  |  |  | -224 | -397 | -886 | -415 | -621 | -844 | 0 |  |  | -3387
CILT Newsletters - Bulletins and Local Newsletters |  |  |  | -281 | -485 | -563 | -502 | -463 | -395 | -280 |  |  | -2969
Workstream 3
Build an "off the shelf" consultancy model for BSP's to use | [12 empty] | 0
Train BSPs in consultancy model and best practice | [12 empty] | 0
Develop roadmap with BSP's and build support mechanism | [12 empty] | 0
Financial support for organisations - Payment to advisors | [8 empty] | -1247 | -7455 | -4602 |  | -13304
BSP Marketing including Translation of materials | [6 empty] | -165 | -211 |  |  |  |  | -376
General Expenses
Almaty office rent | Open since Sept 2019 |  | -555 | -555 | -555 | -602 | -602 | -609 | -609 | -609 | -609 | -609 | -5914
Travel and expenses | Removed cost of CILT INT January visit - Only CILT Kaz travel expenses | -391 | -365 |  |  | -307 | [5 empty] | -407 | -1470
Infrastructure for carrying out training, coffee break | Including Oct-Feb events | -1260 | -278 | [5 empty] | -532 |  |  |  | -2070
Subscriptions - (Zoom, website hosting, Cloud, YouTube marketing, Vkontakte) |  |  |  | -68 | -157 | -340 | -340 | -340 | -278 | -278 | -278 | -105 | -2184
CILT Kazakhstan Project Management, tax included - Total * | This should cover Erbol, Aray, Aibek etc + the govt taxes/insurance etc Is this all staff expenses for the Kaz team | -3515 | -3125 | -2666 | -2666 | -2892 | -2892 | -3181 | -3181 | -2892 | -2892 | -2892 | -32794
CILT International contributions (20% tax included) | £1500 - June/Aug/Dec | [6 empty] | -6676 | -7315 |  |  | -5780 | -19771
Total |  | 133 | 9897 | 4821 | -7359 | -3032.31 | 19126.71 | 2290.7 | -9836.65 | -13193 | 8620.7 | -9945 | 1523.15
Cashflow |  | 0 | 10030 | 14851 | 7492 | 4459.69 | 23586.4 | 25877.1 | 16040.45 | 2847.45 | 11468.15 | 1523.15

## Students Account - 2020
Confirmed students on Diploma programme - Actual Student Account plus Actuals for Membership |  | $1 = 375 kzt - Oct-Jan $1 = 450 kzt - February - May $1 = 415 kzt - June - July $1 = 420 kzt - August $1 = 430 kzt - Sept-Oct
CILT Kazakhstan |  | 2019 |  | 2020 | [11 empty] | 2021
Students account |  | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
| Opening balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | TOTAL | Notes
Revenue
Phase I income |  | 568 | 3738 | 4862 | 10903 | [11 empty] | 20071
Revenue from Level 5 Diploma Students (English and Russian Diploma) |  | 1800 | 5000 | 400 | 2160 | 667 | 1667 | 1222 | 2330 |  | 728 |  | 535 | 1046 | 5813 | 4051 | 27419
Expenses
Student registration fee + 20% Tax |  |  |  |  | -4173 | [9 empty] | -3000 |  | -7173
Training room rent |  |  | -248 |  | -536 |  | -467 |  | -223 | [7 empty] | -1474
Trainers salary (including Tax) |  |  | -595 |  | -1072 |  | -1220 |  | -1220 |  | -1314 |  | -653 |  |  | -851 | -6925
Additional adaptation of training materials | [12 empty] | -290 | -488 |  | -465 | -1243
Miscellaneous (marketing materials, printing, certficates, certificate frames, business lunches, business gifts, furniture, office renovation, travel) |  | -691 | -836 | -1539 | -1583 | -53 | [6 empty] | -465 |  | -645 |  | -5812
Accounting services |  | -120 | -120 | -120 | -120 | -100 | -100 | -100 | -100 | -108 | -108 | -107 | -105 | -105 | -105 | -105 | -1623
Bank fees (transaction fees - local and International) |  | -67 | -27 | -279 | -24 | -28 | -8 | -11 | -8 | -8 | -8 | -12 | -8 | -11 | -11 | -11 | -521
Staff salary |  | -1309 | -2933 | -2933 | [12 empty] | -7175
Taxes |  |  |  | -131 | -9962 | [11 empty] | -10093
Financial Audit | [16 empty] | 0
0
Costs and expenses |  | 181 | 3979 | 260 | -4407 | 486 | -128 | 1111 | 779 | -116 | -702 | -119 | -986 | 442 | 2052 | 2619 | 5451
Cashflow |  |  | 4160 | 4420 | 13 | 499 | 371 | 1482 | 2261 | 2145 | 1443 | 1324 | 338 | 780 | 2832 | 5451